## Sheet1
INSPECTION & TEST PLAN (I.T.P) for Cassete 400 , Cassete 550 , Cassete 620
Row | SCOPE | REQUIREMENT | INSPECTION
|  |  | M.I | P.I | T.P.I
1 | DRAWING | Original drawing approval | H | R | R.A
2 | Material certificate | Chemical Analysis/mill Certificate | H | R | R
3 | Dimensional Inspection | Drawing/DT Report | H | R | R.A
4 | Final Inspection | Drawing/DT Reports | H | H.W | H
5 | Performance test | Manufactur Spec | H | H.W | H
6 | Packing Inspection | Q.C Report | H | R | R.A
7 | FINAL BOOK | Q.C Report | H | R.A | R.A
M.I = Manufacturer Inspector;
P.I = Purchaser Inspector;
T.P.I = Third-party inspector;
H: Hold Point = Hold on the production till Client and TPI Inspector performs inspection and supervise the required test
W: Witness Point = Manufacture shall notify client and TPI Inspector but there is no hold on the production;Client can waive this inspection based on his discretion and informs TPI Inspector accordingly.
R: Document Review = Review means Review document, which includes of material test certificates,WPS, PQR, NDT Procedures and etc.
A: Approval
SW: Spot Witness = for items with spot witness manufacture shall notify Client and TPI inspector as fulfilling the monitoring.