## Total
گزارش ماهانه پروژه .... مجتمع جهان فولاد سیرجان منتهی به ....
| شرح عملیات | ضریب وزن نسبی | درصد وزنی از هر فاز | درصد پیشرفت دوره قبل |  |  | درصد پیشرفت طی دوره |  | درصد پیشرفت تاکنون
|  |  |  | Plan | Actual | VAR | Plan | Actual | Plan | Actual | VAR
1 | Engineering
1 | Basic Design
2 | Detail Design
3 | Manuals and Final documents
2 | Procurement
1 | Local procurement
2 | Foreign procurement
3 | Spare Parts
3 | Civil & Construction
1 | General Construction
2 | Civil Works
3 | Architectural Work
4 | Steel Structure
5 | Erection Works
4 | Commissioning
5 | Training
Total

## Engineering
No. | DESCRIPTION | WF% | WF% Absolut | Upto Last Month |  | This Month |  | Cumulative |  | Balance
|  |  |  | Plan | Actual | Plan | Actual | Plan | Actual
1 | Basice
Area 1
Area 2
Area 3
2 | Detail
Area 1
Area 2
Area 3
Total

## TABLE
[17 empty] | In Process Contractor | [7 empty] | In Process Canymes |  | Final Docs |  |  | AFC : Approved For Construction
Description | A |  |  | B |  |  | C |  |  | D |  |  | E |  |  | F | G | H | I | J | K | L | M | N | O | P | Q |  |  | IFA : Issue for Approval
| Total Doc |  |  | Plan Doc |  |  | Issued Base On Plan |  |  | Issued Over Plan |  |  | Delay In Issue(B-C) |  |  | Total Issue(C+D) | Ap/AC/OB/OC | CLOSED | Deam Approve | CO | RJ | CANCLE | Wait For Trans | Received cany mes reply | Wait for MC CO | Received Contractor reply | Final Doc |  |  | IFR : Issue for Review
[16 empty] | In Process Contractor J: Over Due; Final Docs Q: IFI | FI | AFC-OB | FI:FINAL ISSUE
| I | R | A | I | R | A | I | R | A | I | R | A | I | R | A | [14 empty] | IFC : Issue for Construction | bar: F
TOTAL | [29 empty] | ASB : As Built
Architectural
Civil
Electrical
Instrument & Automation
Mechanical
Planning & Control
Process
Quality control
Refractory
Steel structure
Fluid & Piping

## Procurement
No. | DESCRIPTION | WF% | WF% Absolut | Upto Last Month |  | This Month |  | Cumulative |  | Balance
|  |  |  | Plan | Actual | Plan | Actual | Plan | Actual
1 | Foreign
2 | Local
3 | Spare Parts
Total

## Local
Unit | WBS Code | Package No | Equipment Name/ Activity code | MDR Inquiry Code | W.value | MR No | Vendor | Contract No. | Actual Progress | Procurement Services |  |  | 1- Procurement Services | Contract effectiveness | 2- Contract Effectiveness | Vendor engineering | 3-Vendor Document List | Manufacturing/supplying/Inspection |  | 4- Manufacturing/ Inspection | Transportation |  | 5-Transportation | Local Spare Parts | Remark
[10 empty] | 25% |  |  |  | 10% |  | 15% |  | 45% |  |  | 5%
[10 empty] | RFQ | TBE | P.O |  | Effected |  | VDL |  | Raw Material/Manufacturing | Inspection/Release/Packing |  | Delivery At Site | MRS/F.Book
[10 empty] | 20% | 40% | 40% |  | 100% |  | 100% |  | 88.89% | 11.11% |  | 40% | 60%
[10 empty] | 5% | 15% | 25% |  | 35% |  | 50% |  | 90% | 95% |  | 97% | 100%
Local Equipment

## Foreign
Unit | WBS Code | Package No | Equipment Name/ Activity code | MDR Inquiry Code | W.value | MR No | Vendor | Contract No. | Actual Progress | Procurement Services |  |  | 1- Procurement Services | Contract effectiveness | 2- Contract Effectiveness | vendor engineering | 3-Vendor Document List | Manufacturing/supplying/Inspection |  | 4- Manufacturing/ Inspection | Transportation |  |  |  | 5-Transportation | Foreign Spare Parts | Remark
[10 empty] | 25% |  |  |  | 10% |  | 10% |  | 45% |  |  | 10%
[10 empty] | RFQ | TBE | P.O |  | Effected |  | VDL |  | Raw Material/Manufacturing | Inspection/Release/Packing |  | F.O.B | CFR | Custom Clearance | MRS/F.Book
[10 empty] | 20% | 40% | 40% |  | 100% |  | 100% |  | 88.89% | 11.11% |  | 30% | 30% | 30% | 10%
[10 empty] | 5% | 15% | 25% |  | 35% |  | 45% |  | 85% | 90% |  | 93% | 96% | 99% | 100%
Foreign Equipment

## Construction
No. | DESCRIPTION | WF% Absolut | WF% | Upto Last Month |  | This Month |  | Cumulative |  | Balance
|  |  |  | Plan | Actual | Plan | Actual | Plan | Actual
1 | General Construction
1-1 | General
1-2 | Site Moblization
2 | Civil Works
PU01
PU02
PU03
PU04
PU06
PU07
PU08
PU09
PU10
PU12
PU14
PU15
PU16
PU18
PU19
3 | Architectural Work
PU01
PU02
PU03
PU04
PU06
PU07
PU08
PU09
PU10
PU14
PU15
PU16
PU18
4 | Steel structrure Procurement and erection
PU01
PU02
PU03
PU06
PU07
PU09
PU10
PU12
PU14
PU15
PU16
5 | Erection & Installation work
PU01
PU02
PU03
PU04
pu06
PU07
PU08
PU09
PU10
PU12
PU13
PU14
PU15
PU16
PU18
Total

## CIVIL
ActivityiD | Activity Name | %Plan | %Actual | MC % Complete | Var.
General Construction
General
Site Moblization
Civil Works
Area 1
Area 2
...
...
...
Architectural Work
Area 1
Area 2
...
...
...

## Steel Structure
ActivityiD | Activity Name | %Plan | %Actual | MC % Complete | Var.
Steel structrure Procurement and erection
Area 1
Area 2
..
..
..
..
..
..
..
..
..

## Erection Work
Activity ID | Activity Name | %Plan | %Actual | MC % Complete | Var.
Erection Works
Mechanical
Electrical
Instrument & Automation
Piping & Ducting
Refractory